## Cover Page
Library Management System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Library management system Project ID:A054 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Registration | User/Librarian/Admin | As a user/Librarian, I should be able to register to this website | 1. Clicking on the “Register” button should open the Registration form. 2. User to fill the basic attributes: First Name Last Name DoB Gender Contact Number Email Category User Id Password User Category - User / Librarian 3. Clicking ‘Submit’ button should validate the datatype constraints for each field 4. User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field validation, save the information in the database 6. Upon saving the information in the database, display the message “New user created successfully” 7. For User category Librarian, Library ID field should be auto generated and updated for successful Registration. 8. Librarian registration requests will be sent to Admin for approval and only after approval, he will be able to login. | Critical
US_2 | User Authentication | User/Librarian | As a User/Librarian, I should be able to log in | 1. Clicking “Sign In” link should allow the user to enter the User ID and Password and click 2. Portal to validate the entered user credentials against the database and allow login for registered users. 3. If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching" | Critical
US_3 | Admin credentials | Admin | As a Admin, I should be able to log in | 1. System should have an Admin Login credentials stored in the DB. User Category - Admin 2. When keyed in with correct credentials, it should log in. 3. If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching" | Critical
US_4 | View librarian details | Admin | As an Admin, I should be able to view librarian details. | 1.Admin on clicking “view librarian details ” link should redirect to librarian details page. 2.Admin should be able to view the librarian details 3- librarian id, Librarian name, email id etc can be displayed | Critical
US_5 | Librarian Registration approval | Admin | Ability of the system to allow Admin to view, approve / reject registration request. | 1. Admin should be able to view the new Librarian who have registered by clicking New requests link. 2. Admin should be able to view the complete details by clicking the registration request. 3 Admin should be able to approve / reject the registration Request. 4. If rejected, the Librarian should not be allowed to login with the registered credentials. 5. On rejection, if they try to login, they should get Message "Registration Rejected" 6. On approval they should be able to log in successfully. 7. When the Registration request is awaiting processing by Admin, on login, they should get a message "Registration awaiting approval" | Critical
US_6 | Update librarian details | Librarian | As Librarian, I should be able to update the librarian details. | 1.Librarian should be able to update the librarian details available in the DB. 2. On successful login, he should be able to update the details like Library Name, Address etc. This should be mapped to the Librarian ID created during registration. 3.On clicking Submit, after validation the details should be saved successfully. | Medium
US_7 | Add books | Librarian | As a Librarian, I should be able to add books. | 1.Librarian on clicking “Add books” link should redirect to add books details page. 2.Librarian should be able to add the books and the competency. 3-Book id, book number, book name, author, book category etc can be the fields 4. Book category should be a drop down. The data listing for this drop down should be mocked up and stored in the DB | Critical
US_8 | View books | Admin/Librarian | As an Admin/Librarian, I should be able to view books. | 1.Admin on clicking “view books” link should redirect to book details page. 2. Admin to view books should select the Library Name / Librarian ID to view the details of that Library 3.Admin should be able to view the book details and the availability. Category based list should also be available 4.Librarian on clicking “view books” link should redirect to book details page. 5.Librarian should be able to view the book details and the availability. Category based list should also be available | Critical
US_9 | Update book details - Issue and returned books | Librarian | As an Librarian, I should be able to update the books details. | 1. Librarian on clicking issue book should redirect to the Book issue page. 2. On entering the User Mobile number, the details like User Name, Email should be auto pupulated. Book issued date also should be auto populated from the system date. Book retrun date will be 15 days from the date of issue. That should be calculated and auto populated. 3. He should be able to enter the Book name 4. Clicking Issue Book should update the status of the book as Not availabe. Next available date should be auto populated and it will be the next day of the Book return date. Books issued to filed shoud have the User Name. 5. Librarian on clicking Return books should pop up a field asking for User Mobile Number. 6. On entering the mobile number, it should list all the books issued to the user. 7. He can select the book name and on clicking Returned, should update the status of the Book as avaialbe and details mapped to the user should be nullified. | Critical
US_10 | Issued books | Librarian | As Librarian, I should be able to view the issued books. | 1.On clicking “issued book” link should redirect to the book details page. 2.Librarian should able to view the book details. | Critical
US_11 | Report Generation | Admin | As an Admin, I should be able to generate report. | 1.Admin on clicking the Report generation link should display all the library name list. 2. Selecting the Library Name, He should be able to generate report of the books based on category, Usage 3. He should be able to generate Monthly report of the Lend books by selecting the Month. This can be available for that current year only. 2. Report should be downloadable in excel format | Low
US_12 | Password reset / Forgot User ID | User / Librarian | As a user I should be able to reset password, retrieve User ID | 1. During registration, System should pop up three secret questions for Password recovery. 2. When the user clicks Forgot User ID, system should ask for the secret questions, Phone number / email. On answering the questions correctly, the User ID should be displayed. 3. When the user clicks Forgot Password, system should ask for the User ID and secret questions. On answering the questions correctly, the password reset page should be displayed. 4. On entering the details in the password reset page, password should be validated 5. On clicking Submit, the details should be saved to the Database | Medium
US_13 | User page | User | As User , I should be able to view the book details | 1-User on log in should be able to see the details of the books he has lended. 2-User should be able to see the date of the book lended and the date of return 3-Reminder message (As a pop up) should be displayed 2 days before the date of return 4-User should be able to view the history of all the books he has lended. | Critical
US_14 | Search Books | Admin/Librarian/User | All the users should be able to search for books | 1- All users of the system should be able to search for the books. 2-Users shoud be able to search based on author, Book name, subject etc. 3. The details of the book and the availability status should be displayed. If not available, then next available date also should be displayed | Critical
US_15 | Sort and Filter options | Admin/Librarian/User | All the users should have sort and filter option | 1- Sort and filter options should be available for all users based on the Book category, Book availability, Rating, Author etc | Medium
US_16 | User Norms | Librarian/User | As a Librarian, I should be able to update User norms | 1-Librarian should be able to add/ update/delete dos and donts list in the user norms page 2- User should be able to view the user norms page | Critical
US_17 | User Feedback | User | As User , I should be able to fill feed back form | On clicking Log off , the Message to take up survey should pop up. The user should have the option to take up the survey or not. User should be able to fill in his feedback and submit it. This pop up should appear for every log off click until he submits the feedback. After the feedback is given this pop up should be disabled. | Low
US_18 | Add Feedback form | Admin | As Admin I want to add feeback questionnaires | When Admin clicks add Feedback, it should available in the system On clicking the library details , it should redirect to the Feedback form Admin should be able to fill in the the ratings Attached is the sample feedback questinnaires. This can be modified as required | Low
US_19 | Log off | Admin/Librarian/User | As users I we want to log off | System should disconnect on clicking Log off. | Critical

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000